## Project Resource Tracker
Project Resource Tracker - Skyler Chen (Engineering)
Author: Skyler Chen ¦ Role: Engineer ¦ Location: Fremont ¦ Date: 2025-02-22
Project | Milestone | Owner | Planned | Actual | Status | Resources
Proj Alpha | M1 - Design | Team A | 2025-02-01 | 2025-01-29 | Done | 4
Proj Beta | M2 - Build | Team B | 2025-03-15 | 2025-03-20 | Delayed | 6
Proj Gamma | M1 - Design | Team C | 2025-04-01 | 2025-04-01 | On Track | 3
Proj Delta | M3 - Test | Team A | 2025-05-01 |  | At Risk | 5